## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% | 63.16% | 21.05% | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 10 mi | 67% | 40% | 26.67% | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi | 6 mi | 50% | 50% | 0% | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% | 40.91% | 31.82% | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi | 30 mi | 38% | 30% | 7.5% | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 | 2 | 2 | 40% | 40% | 0% | No new substations completed. Delay in electrical components impacts schedule.
Budget
|  | Budget ($M) | Actual ($M) | Projected ($M)
| M1 | 20 | 22 | 22
| M2 | 50 | 55 | 55
| M3 | 75 | 80 | 80
| M4 | 100 | 110 | 100
| M5 | 120 | 90 | 125

## Dashboard
Metroville Urban Rail Expansion Project Dashboard
| KPIs Monthly Track Installation Progress Electrification Infrastructure Completion Rate Community Engagement Index |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Phase 1
Phase 2
Phase 3
Phase 4
PHASE 1
| Progress - Completion % | [8 empty] | Project Financials
| Status Update |  | Challenges
| Track Installation Progress: The team has installed 4 additional miles in the Southeastern Quadrant, showing an improvement in pace due to equipment upgrades. Electrification Milestones: Achieved significant progress by electrifying an extra 6 miles of track, indicating effective management of the electrification phase despite component delivery delays. |  | - Eastern section in risk - Delay due to rocky terrain - 6mi behind schedule ACTION: in progress evaluation of alternative method to expedite progress. - Overspent in the excavation ACTION: Savings on materials have offset this, keeping us within 5% of our overall budget projection for this phase. - Substations construction: Delay in electrical components ACTION: action plan in progress with Buyer
| Community Feedback Highlights |  |  | Eastern Section Standstill: Persistent challenges with the rocky terrain have led to no progress in track installation, posing a risk to the project timeline and necessitating innovative solutions. Substation Construction Delays: A halt in the construction of substations due to delayed delivery of electrical components threatens to disrupt the planned electrification schedule. Budget Overruns: The actual costs exceeding budgeted amounts in the initial milestones could signal a trend that, if not managed, may lead to significant budget overruns as the project progresses.
Our efforts to engage with the community have been well-received, with many expressing appreciation for our transparency and the opportunity to voice their concerns.
Noise Concerns: There's been a significant increase in complaints about nighttime construction noise in the Eastern Section. Residents are requesting that we limit work to daytime hours.
Add electrification progress
Add budget tracking